## Sheet1
Martial Arts Gym Information Tracking System
Use Case Control ID
id | Use Case | Front-end | status | Back-end | status
3.2.1.1 | The user must be able to register an account | Sir Angel | done wk2 | Francis | done wk2
3.2.1.2 | System user must be able to securely login | Angel | done wk2 | Angel | done wk2
3.2.1.3 | System user must be able to logout from their account | Angel | done wk2 | Angel | done wk2
3.2.1.4 | System must be able to close a session after the session has ended |  |  | Francis | done wk8
3.2.2.1 | The member must be able to view a list of all the courses | Sir Angel | done wk6 | Francis | done wk2
3.2.2.2 | The member must be able to enroll to a course | Sir Angel | done wk6 | Francis | done wk3
3.2.2.3 | The member must be able to cancel a subscription membership from a course | Sir Angel | done wk6 | Francis | done wk3
3.2.2.4 | The member must be able to view a list of announcments | Sir Angel | done wk8 | Francis | done wk2
3.2.2.5 | The member must be able to view their own profile where their identification(QR Code) is located. | Sir Angel | done wk4 | Francis | done wk2
3.2.2.6 | The member must be able to edit their account information. | Sir Angel | done wk4 | Francis | done wk2
3.2.2.7 | A member must be able to check in to a session that an instructor has started, so that they will be recorded in the attendance. | Sir Angel | done wk8 | Francis | done wk6
3.2.2.8 | The member must be able to send feedback regarding the session that he/she has attended | Sir Angel | done wk8 | Francis | done wk8
3.2.3.1 | Instructor must be able to register a new member account | Lilian | done wk6 | Francis | done wk2
3.2.3.2 | The instructor must be able to enroll members to a course | Lilian | done wk6 | Francis | done wk3
3.2.3.3 | The instructor must be able to remove a member from a course | Lilian | done wk6 | Francis | done wk3
3.2.3.4 | Instructor must be able to view the course schedule | Lilian | done wk4 | Francis | done wk4
3.2.3.5 | Instructor must be able to activate a session. | Lilian | done wk4 | Francis | done wk4
3.2.3.6 | Instructor must be able to scan a member's identification(QR code). | Lilian | done wk7 | Francis | done wk6
3.2.3.7 | The instructor must be able to view session feedback submitted by students | Lilian | done wk8 | Francis | done wk8
3.2.3.8 | Instructor must be able to send an announcement to the members of the gym. | Lilian | done wk7 | Francis | done wk6
3.2.3.9 | Instructor must be able to view announcment. | Lilian | done wk4 | Francis | done
3.2.3.11 | Instructor must be able to delete the announcment that he/she has created | Lilian | done wk6 | Francis | done wk6
3.2.3.12 | Instructor must be able to view session attendance summary. | Lilian | done wk7 | Francis | done wk6
3.2.3.13 | Instructor must be able to view all schedule that can be activated in a day. | Lilian | done wk4 | Francis | done wk4
3.2.4.1 | Administrator must be able to view session attendance summary. | Aldwini | done wk8 | Francis | done wk6
3.2.4.2 | Administrator must be able to create a course. | Aldrin | done wk5 | Francis | done wk2
3.2.4.3 | Administrator must be able to view course information. | Aldrin | done wk4 | Francis | done wk3
3.2.4.4 | Administrator must be able to edit course information. | Aldrin | done wk4 | Francis | done wk3
3.2.4.5 | Administrator must be able to remove courses. | Aldrin/Lilian | done wk2 | Francis | done wk2
3.2.4.6 | Administrator must be able to add an instructor. | Aldrin | done wk2 | Francis | done wk2
3.2.4.7 | Administrator must be able to view instructor information. | Aldrin | done wk2 | Francis | done wk2
3.2.4.8 | Administrator must be able to edit instructors that were added. | Aldrin | done wk2 | Francis | done wk2
3.2.4.9 | Administrator must be able to remove instructor. | Aldrin | done wk2 | Francis | done wk2
3.2.4.10 | Administrator must be able to add new members. | Aldrin | done wk2 | Francis | done wk2
3.2.4.11 | Administrator must be able to view and review members' information. | Aldrin | done wk2 | Francis | done wk2
3.2.4.12 | Administrator must be able to must be able to edit members that were added. | Aldrin | done wk2 | Francis | done wk2
3.2.4.13 | Administrator must be able to delete member accounts from the system | Aldrin | done wk2 | Francis | done wk2
3.2.4.14 | Administrator must be able to send announcements. | Aldrin | done wk2 | Francis | done wk 6
3.2.4.15 | Administrator must be able to view announcements. | Aldrin | done wk2 | Francis | done wk2
3.2.4.16 | Administrator must be able to delete announcements. | Aldrin | done wk2 | Francis | done wk6
3.2.4.18 | Administrator must be able to set up membership types within courses. | Aldrin | done wk5 | Francis | done wk3
3.2.4.19 | Administrator must be able to view membership types within courses. | Aldrin | done wk5 | Francis | done wk3
3.2.4.20 | Administrator must be able to edit membership types within courses. | Aldrin | done wk5 | Francis | done wk3
3.2.4.21 | Administrator must be able to remove membership typs within courses. | Aldrin | done wk5 | Francis | done wk3
3.2.4.22 | Administrator must be able to assign instructors accounts to courses. | Aldrin | done wk4 | Francis | done wk3
3.2.4.23 | Administrator must be able to remove instructors from courses. | Aldrin | done wk4 | Francis | done wk3
3.2.4.24 | Administrator must be able to enroll member accounts to courses. | Aldrin | done wk4 | Francis | done wk3
3.2.4.25 | Administrator must be able to remove member accounts from courses. | Aldrin | done wk4 | Francis | done wk3
3.2.4.26 | Administrator must be able to add an additional schedule to a course. | Aldrin | done wk4 | Francis | done wk3
3.2.4.27 | Administrator must be able to delete a schedule from a course | Aldrin | done wk4 | Francis | done wk3
3.2.4.28 | Administrator must be able to edit a schedule from a course | Aldrin | done wk4 | Francis | done wk3
3.2.4.29 | Email Functionality | Aldrin | done wk8 | Aldrin | done wk8
3.2.4.30 | Admin must be able to view session feedback submitted by students | Aldrin | done wk8 | Francis | done wk8